Student Name:	Weight:	10%

Student ID:	Marks:	/17

Assignment: Project Plan

Background

Now that you have a viable project idea, it’s time to plan how you will execute on the idea.  Follow the instructions below to complete your project plan. Please note this is a live document, and it is expected that you will update this plan throughout the remainder of the course.

Instructions

- This is a team submission.

- You will be provided time in class during week 4 to complete this assignment. However, you will likely need to do work outside of class as well.

- The submission should include a completed version of the this template, along with a plan for sprint 1 using the provided spreadsheet.

- All tasks should be specific, measurable, and time-bound (SMART)

Table of Contents

Assignment: Project Plan	1

Background	1

Instructions	1

Overall Timeline	3

Minimum Viable Product (MVP) Backlog	3

Deliverables Outside of Minimum Viable Product	3

Project Management Methodology	4

Tool	4

Daily/Weekly/Monthly	4

Sprint 1 Plan on a Page	5

Sprint 1 Goal	5

Sprint 1 Backlog	5

Sprint 1 Resource Plan	5

Sprint 1 Stakeholder Communication Plan	5

Sprint 2 Plan on a Page	6

Sprint 2 Goal	6

Sprint 2 Backlog	6

Sprint 2 Resource Plan	6

Sprint 3 Plan on a Page	7

Sprint 3 Goal	7

Sprint 3 Backlog	7

Sprint 3 Resource Plan	7

Sprint 1 Plan	8

Marking Criteria	9

Overall Timeline

The Execution Phase has a fixed schedule of 9 weeks comprised of three sprints.

| Phase | Dates (2026) | Weeks | Class hours per week | Total Class hours | Additional hours expected per week | Total Additional hours expected | Total hours per student |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Feb 5-Feb 28 | 3 | 5 | 15 | 4-7 | 12-21 | 27-36 |
| Sprint 2 | March 1-March 20 | 3 | 5 | 15 | 4-7 | 12-21 | 27-36 |
| Sprint 3 | March 21-April 10 | 3 | 5 | 15 | 4-7 | 12-21 | 27-36 |
| Total |  |  |  | 45 |  | 36-63 | 81-108 |

Minimum Viable Product (MVP) Backlog

Listed in the table below are our User Stories that have a Priority of “Must” (not “Should” or “Could”) in our overall Product Backlog (see Business Canvas document).

Collectively, these User Stories constitute the feature set required for a Minimum Viable Product for the solution we are proposing.

The User Story ID should be CONSISTENT with the numbering used in the Product Backlog.

| User Story ID | As a… | I want to be able to… | So that… |
| --- | --- | --- | --- |
| User Story ID | As a… | I want to be able to… | So that… |
| US1 | Customer | get cybersecurity support answers 24/7 from the chatbot | I don’t need to wait for business hours |
| US2 | Customer | ask questions in natural language | I can explain my issue easily |
| US4 | Customer | choose a request type (phishing, suspicious login, VPN, MFA, endpoint alert) | the chatbot can guide me faster |
| US9 | Service Agent / SOC Analyst | collect required incident details through guided questions (slot filling) | tickets are complete and easier to triage |
| US11 | IT / Security Admin | enforce separation between enterprise data and public AI | sensitive data is protected |
| US12 | IT / Security Admin | restrict internal KB access by role/group (RBAC) | users only see approved content |

Deliverables Outside of Minimum Viable Product

Listed in the table below are deliverables you must complete or update for each sprint. These deliverables are deliberately not included with the Minimum Viable Product Backlog (above) as they do not represent features of the product. When you plan for a sprint, ensure to allocate time to completing these deliverables.

| # | Deliverable | Description |
| --- | --- | --- |
| (1) | Updated Documentation | Ongoing updates to the business canvas and project plan |
| (2) | Sprint Progress Report | One progress report per sprint |
| (3) | Solution Showcase | One showcase per sprint |

Project Management Methodology

Use Activity - Selecting a Project Management Methodology, found in Brightspace, to review different project management methodologies.

The course is structured to use an Agile approach. A tracking spreadsheet has been provided for you.

What additional methodologies and/or tools will you use to manage your project, and why?

We will follow an Agile Scrum approach (3 sprints) and use lightweight project controls to keep work visible and on track. Our primary tools will be: Microsoft Teams (communication and meeting notes), the provided sprint tracking spreadsheet (task breakdown, hours, status), and OneDrive (document version control). For technical work and change tracking, we will use GitHub (source control, issue tracking, and pull requests). We will also use a simple Definition of Done checklist and a risk/issue log to manage scope, quality, and blockers. These tools help us coordinate work, avoid duplicate effort, and provide clear evidence of progress for sprint reviews.

Daily/Weekly/Sprintly

Given your methodology and tools, how will members use the above project tools on a daily, weekly, and sprint basis?  Be specific, include things like meeting agendas

Daily (10–15 minutes, Teams): quick stand-up. Agenda: (1) What I completed since last check-in, (2) What I will do next, (3) Blockers/risks, (4) Update tasks/hours in the sprint spreadsheet. Weekly (45–60 minutes, Teams): working session + progress review. Agenda: (1) Demo current build or key artifacts, (2) Review backlog and adjust priorities, (3) Confirm deliverables due (documentation, logs, showcase), (4) Assign tasks for next week, (5) Review risk/issue log. Sprint Planning (start of sprint, 60–90 minutes): define sprint goal, select MVP backlog items, break stories into tasks ≤3 hours, assign owners and estimate hours (27–36 per member). Sprint Review/Showcase (end of sprint, 30–60 minutes): demonstrate completed user stories, show evidence (screenshots/logs), and gather feedback. Sprint Retrospective (end of sprint, 20–30 minutes): what went well, what didn’t, and 2–3 action items to improve next sprint.

Sprint 1 Plan on a Page

Sprint 1 Goal

What are we trying to accomplish?

By the end of Sprint 1, we want to have accomplished these things:

|  | Goal |
| --- | --- |
| 1 | A working chatbot MVP that can answer cybersecurity questions with basic “24/7 support” behavior (US1). |
| 2 | Natural language Q&A working end-to-end (user types normal sentences → system returns an answer) (US2). |
| 3 | Request type selection implemented (phishing / suspicious login / VPN / MFA / endpoint alert) and passed into the chat workflow (US4). |
| 4 | Initial FAQ knowledge base integrated so common repetitive questions are handled by the bot (US7). |
| 5 | Basic security controls in place: enterprise data separation + role-based access (RBAC) concept demonstrated with at least 2 roles (US11, US12). |

Sprint 1 Backlog

What product backlog stories will we complete?

To achieve the Sprint Goal, these stories must be completed:

The User Story ID should be CONSISTENT with the numbering used in the Product Backlog.

| User Story ID | As a… | I want to be able to… | So that… |
| --- | --- | --- | --- |
| 1 | Customer | get cybersecurity support answers 24/7 from the chatbot | I don’t need to wait for business hours |
| 2 | Customer | ask questions in natural language (not exact keywords) | I can explain my issue easily |
| 4 | Customer | choose a request type (phishing, suspicious login, VPN, MFA, endpoint alert) | the chatbot can guide me faster |
| 7 | Service Agent / SOC Analyst | have repetitive FAQs handled by the chatbot | I can focus on investigation work |
| 11 | IT / Security Admin | enforce separation between enterprise data and public AI | sensitive data is protected |
| 12 | IT / Security Admin | restrict internal KB access by role/group (RBAC) | users only see approved content for them |
| 15 | Knowledge Base Owner | upload and organize runbooks/FAQs/playbooks for indexing | the bot has enough approved content to answer |

Sprint 1 Resource Plan

Who will do what to accomplish our goal?

| Team Member | What tasks the Team Member will commit to work on |
| --- | --- |
| Li | Build the website/chat interface MVP (chat UI + request type selector). Connect frontend to backend API. Support integration testing for US1/US2/US4. |
| Keto | Set up RAG retrieval: prepare KB format, define chunking/metadata, configure search + retrieval settings, and test retrieval quality using FAQ questions (US1/US2/US7). |
| Doris | Build Flow Control / Orchestrator (Azure Function): implement /chat API, connect retrieval + LLM, return answers with citations structure, add basic RBAC filtering rules (US11/US12), and support end-to-end testing. |
| Ayo | Create FAQ + Policy content for Sprint 1: initial FAQ set by request type, basic chatbot policy boundaries, and content labels for public/internal to support RBAC filtering (US7/US11/US12). |

Sprint 1 Stakeholder Communication Plan

How will we communicate with our stakeholders?

| Stakeholder | What do they need to know | Frequency |
| --- | --- | --- |
| Instructor | Sprint 1 progress, which backlog items are completed (US1/2/3/4/7/11/12/15), demo readiness, and blockers/risks. | Weekly (end-of-week update) |
| Product Owner (Simulated – FortiAnswer Enterprise) | Confirm Sprint scope and priorities, approve request types, review chatbot behavior and security boundaries (public vs internal), and accept Sprint 1 demo features. | Once per Sprint (mid-sprint review) + end-of-sprint demo |
| Internal Team (Li/Keto/Doris/Ayo) | Progress updates, task ownership, integration issues, and next steps for the demo. | 2–3 times per week (short standup) |
| End Users (Simulated Customer + Agent personas) | Feedback on whether answers are clear/helpful/safe, and whether the request-type flow makes sense. | Once per Sprint (feedback session) |

Sprint 2 Plan on a Page

Sprint 2 Goal

What are we trying to accomplish?

By the end of Sprint 2, we want to have accomplished these things:

|  | Goal |
| --- | --- |
| 1 | Ticket escalation working: customers can create a security support ticket when the bot can’t resolve the issue (US6). |
| 2 | Guided incident intake (slot filling): the bot collects required details through structured questions so tickets are complete (US9). |
| 3 | Auto-summary for agents when a chat escalates (what happened, device, indicators, urgency) to reduce repeated questions (US8). |
| 4 | Severity tagging implemented (low/medium/high) based on rules so high-risk cases are prioritized (US10). |
| 5 | Safe response controls for restricted topics (credentials, sensitive incident details) to reduce privacy/compliance risk (US13). |
| 6 | Fast policy publishing workflow: business/policy owners can update policies/playbooks quickly and updates are reflected in the knowledge base (US14). |
| 7 | Conversation logging for audit/troubleshooting: log outcomes (answered/escalated/ticket created) (US19). |

Sprint 2 Backlog

What product backlog stories will we complete?

To achieve the Sprint Goal, these stories must be completed to achieve the sprint goal:

The User Story ID should be CONSISTENT with the numbering used in the Product Backlog.

| User Story ID | As a… | I want to be able to… | So that… |
| --- | --- | --- | --- |
| 6 | Customer | create a security support ticket if my issue is not resolved | I still get help even when the bot can’t solve it |
| 8 | Service Agent / SOC Analyst | receive an auto-summary when a chat escalates (what happened, device, indicators, urgency) | I don’t need to ask the same questions again |
| 9 | Service Agent / SOC Analyst | collect required incident details through guided questions (slot filling) | tickets are complete and easier to triage |
| 10 | SOC Analyst | tag the request with severity (low/medium/high) based on rules | high-risk cases get handled faster |
| 13 | Compliance Officer | require safe responses for restricted topics (credentials, sensitive incident details) | we reduce compliance and privacy risk |
| 14 | Business Manager / Policy Owner | publish new or updated policies/playbooks to the knowledge base quickly | the chatbot stays aligned with the latest rules |
| 19 | IT / Security Admin | log conversations and outcomes (answered/escalated/ticket created) | we can audit and troubleshoot issues |

Sprint 2 Resource Plan

Who will do what to accomplish our goal?

| Team Member | What tasks the Team Member will commit to work on |
| --- | --- |
| Li | Update the website UI to support escalation: “Create Ticket” button, guided question UI for slot-filling, and display ticket ID + status. Support agent-view display for auto-summary. |
| Keto | Enhance RAG content and retrieval to support escalation flows: define ticket categories, required fields per request type, update KB structure for policy publishing (US14), and help design severity rules input text. |
| Doris | Implement backend/orchestrator logic: ticket creation API, slot-filling state management, auto-summary generation, severity tagging rules engine, conversation logging (US6/8/9/10/19), and integrate safe-response checks (US13). |
| Ayo | Build policy/compliance content: restricted-topic rules and examples, safe-response guidelines (US13), publish/update workflow documentation (US14), and create test cases for severity + escalation scenarios. |

Sprint 2 Stakeholder Communication Plan

How will we communicate with our stakeholders?

| Stakeholder | What do they need to know | Frequency |
| --- | --- | --- |
| Instructor | Sprint 2 progress, completed stories (US6/8/9/10/13/14/19), demo readiness (ticket + escalation flow), and blockers/risks. | Weekly (end-of-week update) + end-of-sprint demo |
| Product Owner (Simulated – FortiAnswer Enterprise) | Confirm escalation workflow meets needs (ticket + required fields), approve severity rules approach, and accept Sprint 2 features. | Mid-sprint review + end-of-sprint acceptance/demo |
| Internal Team (Li/Keto/Doris/Ayo) | Integration checkpoints (UI ↔ API ↔ KB), testing status for escalation + compliance, and demo script readiness. | 2–3 times per week (short standup) |
| User Persona Reviewers (Simulated Customer + Agent) | Validate usability: guided questions are clear, ticket summary is helpful, severity tagging makes sense, and safe responses behave correctly. | Once per Sprint (guided test session) |

Sprint 3 Plan on a Page

Sprint 3 Goal

What are we trying to accomplish?

By the end of Sprint 3 we want to have accomplished these things:

|  | Goal |
| --- | --- |
| 1 | Content refresh / re-index capability so knowledge base updates don’t become outdated (US16). |
| 2 | User feedback collection: customers can rate answers (helpful / not helpful) and leave comments to support continuous improvement (US17). |
| 3 | Basic analytics dashboard/report showing top questions, deflection rate, and escalation rate to measure chatbot value (US18). |
| 4 | Preferred responses management: agents can maintain a set of approved responses for common security issues to keep answers consistent (US20). |
| 5 | Screenshot / error message upload during chat to improve troubleshooting and ticket quality (US21). |

Sprint 3 Backlog

What product backlog stories will we complete?

To achieve the Sprint Goal, these stories must be completed to achieve the sprint goal:

The User Story ID should be CONSISTENT with the numbering used in the Product Backlog.

| User Story ID | As a… | I want to be able to… | So that… |
| --- | --- | --- | --- |
| 16 | Knowledge Base Owner | refresh/re-index content on a schedule or after updates | answers don’t become outdated |
| 17 | Customer | rate the answer (helpful / not helpful) and leave feedback | we can improve the bot over time |
| 18 | Business Manager | view basic analytics (top questions, deflection, escalation rate) | we can measure the value of the chatbot |
| 20 | Service Agent Lead | maintain a set of “approved responses” for common security issues | answers stay consistent across the team |
| 21 | Customer | upload a screenshot or error message during chat | troubleshooting becomes easier |

Sprint 3 Resource Plan

Who will do what to accomplish our goal?

| Team Member | Significant tasks Team Member will commit to work on |
| --- | --- |
| Li | UI updates: add file upload (screenshot/error), add rating + feedback form, and create basic analytics view page (charts/tables). |
| Keto | KB maintenance and indexing: define re-index workflow, ensure updated content is properly chunked/tagged, and support “preferred responses” content format for retrieval. |
| Doris | Backend/orchestrator enhancements: implement feedback storage, file upload handling (store + link), logging fields needed for analytics, and schedule-triggered re-index job integration (US16/17/18/21). |
| Ayo | Content governance: define preferred responses library (templates + wording), review analytics definitions (what counts as deflection/escalation), and create testing scenarios for feedback + upload + reindex. |

Sprint 3 Stakeholder Communication Plan

How will we communicate with our stakeholders?

| Stakeholder | What do they need to know | Frequency |
| --- | --- | --- |
| Instructor | Sprint 3 progress, completed stories (US16/17/18/20/21), demo readiness (feedback + analytics + upload), and final project readiness. | Weekly update + final end-of-sprint demo |
| Product Owner (Simulated – FortiAnswer Enterprise) | Confirm analytics metrics are meaningful, approve preferred responses governance approach, and accept Sprint 3 “improvement + measurement” features. | Mid-sprint review + end-of-sprint acceptance/demo |
| Internal Team (Li/Keto/Doris/Ayo) | Integration alignment: feedback data model, upload storage approach, re-index schedule, analytics calculations, demo script. | 2–3 times per week (short standup) |
| User Persona Reviewers (Simulated Customer + Agent) | Validate usability: feedback flow is easy, upload works smoothly, analytics outputs are understandable, preferred responses improve consistency. | Once per Sprint (guided test session) |

Sprint 1 Plan

Using the chosen project methodology and any relevant tools, plan out your first sprint.

- Use the spreadsheet provided.

- All team members should have 27-36 hours of tasks planned.

- No task should be longer than 3 hours.  If so, break it into sub-tasks.

- Please refer to the rubric for details.

- Each group should also maintain a Research Log and an AI Log throughout the sprint.  Please put this in a separate document in your teams site

Research Log:

| Team Member | Topic | Source | URL | Date |
| --- | --- | --- | --- | --- |

AI Log

| Team Member | AI Tool | Purpose | Date |
| --- | --- | --- | --- |

Marking Criteria

| Criteria | 4 | 3 | 2 | 0 |
| --- | --- | --- | --- | --- |
| Minimum Viable Product | The stories chosen from the product backlog form a clear minimum viable product that solves a compelling problem. Enough stories are chosen for adequate complexity, however few enough that the goal is clear. | The stories chosen from the product backlog form a minimum viable product that solves a problem. Enough stories are chosen for adequate complexity, however few enough that the goal is reasonably clear. | The stories chosen from the product backlog could form a minimum viable product that solves a problem. | There is no minimum viable product, or the stories chosen could not form a minimum viable product. |
| Project Management Methodology | Adequate research was put into choosing the project methodology, and there are clear expectations set for how procedures will be managed on a daily, weekly, and monthly basis. | Adequate research was put into choosing the project methodology, and there are expectations set for how procedures will be managed on a daily, weekly, and monthly basis. | A project methodology was chosen, and how the project will be managed is described, although clarification may be required. | A project methodology was not chosen, or it is unclear how the project will be managed. |
| Criteria | 3 | 2.25 | 1.75 | 0 |
| Sprint Plans | There is clear thought behind the stories the team intends to complete each sprint, and a mixture of must do and should do items for each sprint. Each team member has a number of key objectives. It is very clear who the stakeholders involved with each sprint are and how they will be communicated with. | There is thought behind the stories the team intends to complete each sprint, and a mixture of must do and should do items for each sprint. Each team member has a number of key objectives. It is clear who the stakeholders involved with each sprint are and how they will be communicated with. | There is thought behind the stories the team intends to complete each sprint. Most team members have a number of key objectives. Most stakeholders involved with each sprint are listed. | The sprint planning is unclear, not all members have stories assigned, or stakeholders are not correctly identified. |
| Criteria | 6 | 4.5 | 3 | 0 |
| Plan for Upcoming Sprint | Using the proposed project methodology, the team has planned tasks that will ensure each team member has at least 25-30 hours of work for the next sprint. Tasks are written in a SMART format. Larger tasks are broken down into smaller sub-tasks. It is clear what members plan to do on a week by week basis. | Using the proposed project methodology, the team has planned tasks that will ensure each team member has at least 25 hours of work for the sprint ahead. Tasks are written in a SMART format. Larger tasks are broken down into smaller sub-tasks. It is clear what members plan to do during the next sprint. | Using the proposed project methodology, the team has planned tasks that will ensure each team member has at least 20 hours of work for the next sprint. | A plan was not completing using the chosen methodology, or there is less than 20 hours per team member for the next sprint. |